## Project Progress
PROJECT CHARTER - PROGRESS TRACKER
CUSTOMER SESSION PORTAL
Weeks | Entry Filled by | Expected outcome | Actual Completion | Stage of the project charter | % of completion | Challenges (If any)
Week-1 |  |  |  |  | 25%
Week-2 |  |  |  |  | 50%
Week-3 |  |  |  |  | 75%
Week-4 |  |  |  |  | 100%
Week-5
Note on B3: Priyadharshini Vivekanandan Gopal: Name of the person, updating the field
Note on C3: Priyadharshini Vivekanandan Gopal: Discuss with your mentor and update the no.of task to be completed for the particular week
Note on D3: Priyadharshini Vivekanandan Gopal: Before Every Monday - actual completion of task to be mention
Note on E3: Priyadharshini Vivekanandan Gopal: Please update the current stage of your project. For your reference below mentioned are stages for project charter (i.e., 1.Requirement Gathering 2. Data Cleaning and Processing 3. Front-end Design/back End Design 4. APIs Design 5. Authentication and Authorization 6. Data Storage 7. Testing and Deployment 8.Continuous Integration/Continuous Deployment (CI/CD)
Note on F3: Priyadharshini Vivekanandan Gopal: Please fill your curren week % of completion

## UI Dev Tracker
| CUSTOMER SESSION MANAGEMENT |  |  |  |  | Software Tools Required |  |  | UI Team
[6 empty] | Vs Code |  |  | Durgam Prashanth
Node.js v14+
Angular CLI v15+
Postman
SN | User Story | Acceptance Criteria | Start Date | End Date | Developer | Support Links | Status | Dependancy
1 | Create Basic Angular Application | 1-Angular v15 must use 2-Configure unit test using jest framework 3-Eslint should be integrated(static code analysing tool), basic eslint rules should be added. 4-Angular material UI library should be installed 5-Basic application layout should be available. 6- Integrate bootstrap in the application. 7- Application should be complete responsive. 8- No errors in browser console 9-All the basic scripts should be added in the application package.json 10- Basic folder structures should be created | 2023-08-03 | 2023-08-04 |  | 1-https://angular.io/quick-start 2-https://medium.com/@kyjungok/setup-jest-in-angular-application-22b22609cbcd 3-https://javascript.plainenglish.io/how-to-configure-eslint-and-prettier-on-angular-application-87dbd767369c | Not Started | NA
2 | Application Header | 1-Create application header with proper height and background color 2- Display application name with proper logo in top left of the header 3- Display user logo at right side of header. 4- Once the user logged in display logged in username along with user logo. 5-Click on user logo will display dropdown menu with login option if not logged in , logout option if already logged in. 6- Header should be completely responsive. |  |  |  | 1-https://getbootstrap.com/docs/4.0/components/navbar/? 2-https://www.truecodex.com/course/angular-material/angular-material-sidenav-and-toolbar-example |  | NA
3 | User Login Page | 1- Create responsive login component / screen based on UX 2- Login page should contain the following fields ( username,password,login button) 3-UI validation with proper error messages (error message if not provided proper input in username password fields) 4-Create/call method for login when user click on login button. 5-Unit test should be written for login method with 90% coverage. 6- Create separate service for login (LoginService) along with unit test. | [5 empty] | Login API
4 | Dashboard | 1-Create new Dashboard component 2-Once the login is success route the application from login screen into dashboard screen. 3-Create Dashboard layout as per UX mock design provided. 4-Implement Active and Archived tabs in table as per design.
5 | Create Session Popup
6 | Edit Session Popup
7 | View Session Popup
8 | Delete Session Popup
9 | Login API Integration
10 | Active / Archive Session API Integration
11 | Edit Session API Integration
12 | Delete Session API Integration
13
14
15
16